## Indetails mivan index
KCC- LG Unit wise Work for billing
Category-
Building -
Type of Unit-
SN | Work Category | Sub Work Category
1 | Mivan
Mivan Centering
|  | Sr no. | Check Point | Hall |  |  |  | Kitchen |  |  |  | M Bedroom |  |  |  | C Bedroom |  |  |  | C. Toilet |  |  |  | Att. Toilet |  |  |  | Washup |  |  |  | Lobby |  |  |  | Stairs
|  |  |  | N | S | E | W | N | S | E | W | N | S | E | W | N | S | E | W | N | S | E | W | N | S | E | W | N | S | E | W | N | S | E | W | Steps | Side
|  | 1 | Slab Level
|  | 2 | Refrence line -1'
|  | 3 | Plumb (Gola)
|  | 4 | Wall Alignment
|  | 5 | Wall Tie
|  | 6 | Pin / Weage
|  | 7 | Window Opening
|  | 8 | Room measurement
|  | 9 | Door Opening measurement
|  | 10 | All Corner 90
|  | 11 | Proper Rocker Fitting
|  | 12 | Props in proper position
|  | 13 | No damage panel
|  | 14 | DP Props Checking
|  | 15 | Outside centering
|  | 16 | All outer Kicker allignment
|  | 17 | Soldier fitting
|  | 18 | Maintain sunk Allignment and measurement
|  | 19 | 100mm Chairs for sunk
|  | 20 | Lift Plumb
|  | 21 | Lift Line
|  | 22 | Lift Diagonia
|  | 23 | Lift All Corner 90
|  | 24 | Lift Kicker Line
|  | 25 | Passage Opening measurement
|  | 26 | Passage / Duct Opening Kicker ( Allignment/measurement/support)
steel/slab beam Reinforcement
|  | Beam No. | Beam Size | Hall E: Bottom Reinforcement; M Bedroom N: Top Reinforcement; C. Toilet S: Stirrups; Att. Toilet W: Cover; Washup S: Check Date
[6 empty] | Bottom Straight Bar |  | Check Date | Bottom Curtail Bar = 0.7*L |  | Check Date | Top Straight Bar |  | Check Date | Extra Bar Left Beam = L/4 |  | Check Date | Extra Bar Right Of Beam = L/4 |  | Check Date | At Support = L/4 |  | Check Date | At Mid Span
|  |  | L | Hall N: B; Hall S: Check; Hall E: No. Bar.; Hall W: dia. of bar; Kitchen S: No. Bar.; Kitchen E: dia. of bar; M Bedroom N: No. Bar.; M Bedroom S: dia. of bar; M Bedroom W: No. Bar.; C Bedroom N: dia. of bar; C Bedroom E: No. Bar.; C Bedroom W: dia. of bar; C. Toilet S: dia. of Stirrups; C. Toilet E: Spacing of Stirrups; Att. Toilet N: dia. of Stirrups; Att. Toilet S: Spacing of Stirrups; Att. Toilet E: Check; Att. Toilet W: Side cover; Washup N: Bottom cover
2 | Electrical Work-I | 1 |  | Kitchen N: 2; Kitchen S: 3; M Bedroom W: 4; C Bedroom S: 5
|  | Slab piping + wall |  | Kitchen N: Conselled box; Kitchen S: Block wiring + Repairing; M Bedroom W: Switch plates; C Bedroom S: Testing
|  | D.B to S.B.Pipe drop + S.B. to point pipe drop + D.B. to meter pipe drop as per drawing | Pipe fitting should be 1/2" inside the wall face | Hall N: Fan hook center position should be after deduction of loft width; Hall S: Every pipe & bend should be tite with pvc solution; Hall E: Every pipe end should be properly close with tape; Hall W: Check every point position as per drawing or not; Kitchen N: Conselled box bottom level 54'' from FFL fitting in line& level; Kitchen S: point +earthing wire =1.5 , mcb box to SB board+15 amp point -2.5; Kitchen E: Check every point wiring at proper position as per drawing; Kitchen W: Wiring from D.B to S.B. + S.B. to light point ,fan point + D.B. to meter pipe drop as per drawing; M Bedroom N: TV wiring done or not; M Bedroom S: Inverter/AC wiring if required; M Bedroom E: All repairing related to electric work should in in proper finish; M Bedroom W: Every plate fitting should be in line & level; C Bedroom N: Every wire shouldbe join propery tight & and in seqence; C Bedroom S: Testing of each and every point is in active position
3 | Electric work - E | 1 |  | Hall N: 2; Hall S: 3
|  | E-7 = Block to parking meter panal pipe fitting |  | Hall N: E-8 = Block to parking meter panal wiring; Hall S: E-9 =Block panel fitting
|  | Pipe fitting should be in line & level and every pipe joint connect with pvc solution | Pipe should be seprate for each flat | Hall N: Contineous Wiring from D.B to parking meter panal without any joint; Hall S: Meter & Main switch fitting; Hall E: Electric supply connected from meter panal to D.B. & testing of Wiring
4 | Water Proofing | 1 |  | Kitchen S: 2
|  | Chipping of Beam | First Coat | Kitchen S: KOBA FINAL COAT
|  | Chipping of Beam 2" below from Slab Top | Cleanning & Washing with water | Hall N: Chemical coating; Hall S: Leakage pipe Fitting; Hall E: Nhani Trap & commod trap fitting; Hall W: 1st coat cement ghotai chemical water proofing plaster; Kitchen N: Water leakage test; Kitchen S: Brick bats Koba Fitting in water proofing cement morter; Kitchen E: Koba finishing with cement ghotai plaster proper with slope towards trap; Kitchen W: At the time of final finishing wall & floor should be right angle and mimi.1.5'' below slab top; M Bedroom N: Testing
5 | Plumbing-I | 1 |  | Hall E: 2; Kitchen S: 3; M Bedroom E: 4; C Bedroom E: 5
|  | SLAB PIPING |  | Hall E: Zari cutting & Hole; Kitchen S: Internal pipe line fitting; M Bedroom E: Pipe line testing & zari repairing; C Bedroom E: Nahani trap fitting
|  | Sluice pipe level | Sluice pipe outlet position as per Commod/Trap/Orisa pan fitting as per drawing at proper position, line & level | Hall N: Dia.of Sluice pipe for hole is 25mm greater than required Commod/Trap/Orisa pan outlet pipe; Hall S: Sluice Pipe slope 1/2" from inner side to outer side; Hall E: Toilet ,kitchen & washup zari cutting as per drawing; Hall W: All zari cutting should be 10 mm extra diamter of pipe; Kitchen N: Commod outlet pipe hole ,Water tank to block supply hole & any other hole as per drawing -; Kitchen S: All outlet connection of Toilet ,kitchen & washup internal pipe line fitting as per drawing; Kitchen E: All Toilet ,kitchen & washup internal pipe line fitting min. 10 mm inside from wall face; Kitchen W: Every joint of Elbow,bend,Tee,Reducer,coupling etc fitting with pvc solution in proper manner; M Bedroom N: Wash basin & Kitchen sink outlet pipe should fitting up to 4 way/2 way nani trap; M Bedroom S: Every outlet point should be close by plug with use of tephlon tape; M Bedroom E: Confirm Every outlet point should be close by plug .; M Bedroom W: All Toilet ,kitchen & washup internal pipe line testing by water pressure pump; C Bedroom N: If any leakage found ,firstly repair and test after repairing; C Bedroom S: if no leakage is confirm , then repair all pipe line with cement ,orter to the face of wall with kata plaster; C Bedroom E: Trap fitting after water proofing coating as per drawing; C Bedroom W: Trap should be fitting with water proofing morter; C. Toilet N: Also water leakge pipe should be fitting with slope towards out side
6
Show Fitting | bar: Hall N to C Bedroom E
|  | Bath/Toilet |  | Hall E: Common toilet; M Bedroom S: Kitchen; M Bedroom W: Wash
|  | Water meter fitting | Shower | Hall N: Wall mixer fitting; Hall S: Trap jali fitting (Gap between jali & Trap pipe is properly fill with water proofing morter); Hall E: Commod Fitting; Hall W: Two way bib cock fitting; Kitchen N: Cisteren fitting; Kitchen S: Angle cock fitting; Kitchen E: Long Body Tap; Kitchen W: Basin fitting; M Bedroom N: Basin piller cock with PVC connection and Basine outlet; M Bedroom S: Sink tap fitting; M Bedroom E: Sink outlet fitting; M Bedroom W: Tap point fitting; C Bedroom N: Washing machine tap fitting; C Bedroom S: Washing machine outlet; C Bedroom E: Trap jali fitting(Gap between jali & Trap pipe is properly fill with water proofing morter)
6 | Plumbing-E | 1 |  | Hall E: 2; Kitchen E: 3; Kitchen W: 4
|  | Rain water pipe fitting |  | Hall E: W.C/Bath/Toilet/Wash. pipe Line fitting; Kitchen E: Water supply line from OHWT; Kitchen W: Water supply line from GWT to OHWT in HDPE pipe
|  | R.W. pipe should be min.1'' below terrace top finish level | Every joint should be fitting with solution in proper manner | Hall N: Pipe Line should in line, level and proper clamping; Hall S: R.W. outlet pipe should be upto R.W.Harvesting pit; Hall E: W.C/Bath/Toilet/Wash. pipe Line should in line, level and proper clamping; Hall W: Every joint should be fitting with solution in proper manner; Kitchen N: W.C/Bath/Toilet/Wash. pipe Linee should be upto sewarage line chember; Kitchen S: Bath and Wash pipe line join to sewarage chember throught Gulley trap; Kitchen E: Water supply pipe from OHWT to flat should be fiiting to water meter.(Dia .of pipe reduce as per plumbing drawing.
7 | Tile | 1 |  | Kitchen E: 2; C Bedroom E: 3
|  | FLOOR TILE |  | Kitchen S: Skirting; Kitchen E: WASH FLOOR TILE FITTING; M Bedroom S: WASH WALL TILE FITTING; C Bedroom E: Kitchen Otta and wall tile
|  | 2' level marking on every room corner | Check All room tile thhiyye as per 25 mm gadi for tile fitting | All room tile should in 00 level | All room tile fitting as per tile flooring drawing and joint should be continue in line & level | Check no dammage tile fitting in any room | Every room should be clean After complition of tile fitting. | All room floor & glazed tile properly acid wash and joint filling completed in all respect | skirting of all room tile should be in line , level, in right angle & even size 3" | Flooring slope should be towards to Nani trap =1'' | Wash floor tile should be below 1'' from kitchen floor tile top at chaukat. | Flooring tile around trap tile should be 4 mm below by flooring tile | Glazed tile fitting in plumb & corner should be in 90 degree . | Wall tile fitting veber should not more than 6 mm | Wall tile should be in line & level. | Joint should be properly fill around the every plumbing point | Floor & Wall tile properly acid wash and joint filling completed in all respect | Kadappa Vertical stand Fitting as per given drawing in right angle ,plumb, line & level. | Marble/ Granite Fitting with Slope towards steel sink | Steel sink fitting should be below granite top | Water Pattiwith polish fitting should be in single piece with line ,level & proper joint filling. | 1.25'' PVC bend fitting for Gas pipe with proper joint filling | Plumbing tab point /outlet pipe fitting is done before wall tile work | Wall tile fitting morter should not more than 6 mm | Wall tile should be in line ,level, plumb & in right angle. | Joint should be properly fill around the sink tap
|  | 4 |  | Kitchen W: 5; M Bedroom W: 6; C Bedroom W: 7
|  | Common toilet floor |  | Hall E: Common toilet wall tile; Kitchen W: Acid Wash; M Bedroom W: Window Seal; C Bedroom W: Kadapa Rack
|  | Flooring slope should be towards to Nani trap =1'' |  | Wash floor tile should be below 1'' from kitchen floor tile top at chaukat. | Flooring tile around trap tile should be 4 mm below by flooring tile | Glazed tile fitting in plumb & corner should be in 90 degree . | Wall tile fitting veber should not more than 6 mm | Wall tile should be in line & level. | Joint should be properly fill around the every plumbing point | Floor & Wall tile properly acid wash and joint filling completed in all respect | If any door or plumbing fitting is done cover all fitting by plastic panni with abro tape fitting before start of acid wash | All room floor & glazed tile properly acid wash | After acid wash joint of all room floor and wall should be properly fill completed in all respect | After filling the joint all room should be properly clean in all respect | All room window sill fitting should be in line & level | All room window sill granite polish should be done in proper finish. | All room window sill fitting should be 4 mm outside the inner face of wall | At the time of window sill fitting outside sloping galtha should be provide of all room . | Firstly marking should be done on wall as per given drawing | All ziri depth should not be less than 10 mm. | All kadappa Fitting as per given drawing | Kadappa Vertical stand Fitting in right angle ,plumb, line & level. | Kadappa shelf Fitting in line & level. | All kadappa edges should be properly polish | After fitting of all kadappa All ziri should be smoth finish as per wall surface
8 | POP | 1 |  | Kitchen N: 2; Kitchen E: 3; M Bedroom E: 4
|  | Basic work |  | Hall N: POP-1 - Pop dhar finish; Kitchen N: POP-2- Framing; Kitchen E: POP-3- Sheet fitting; M Bedroom E: POP-4- Electric light cutting
|  | First check civil work is completed(100%) or not | Check no any leakage where pop will be carry out | Hall N: Each & every dhar of column ,Beam ,loft,door & window jams etc; Kitchen N: Mark even level at 5' height form tile top on every wall; Kitchen S: Framing of pop as per drawing & design; Kitchen E: Make sure wiring of every electric point is at proper position; Kitchen W: Before fitting of pop sheet check fan hook is at proper position; M Bedroom N: Fitting of pop sheet & check every joint of pop sheet is properly fill up without any undulation; M Bedroom S: Each & every dhar of pop in line,level,plumb & right angle; M Bedroom E: Make sure hole cutting of sheet as per ceiling light size & in proper manner
|  |  |  | Right angle | Plumb | Level | Line
9 | Civil Work | 1 |  | Kitchen W: 2
|  | Door Frame Fitting |  | Kitchen W: brick/block work
|  | Hold fast fitting | Chaukat top level | Outer gola | Chaukat patam bottom dutta | Chaukat patam top dutta | Line and face | Door panal opening face | Wall & Frame Gap Filling | Properly jamb Fitting | 100% Rangat compliteted | Column casting | Pardi casting | 1st layer of block work on rangat should in level | Every layer of block work should be in level | Properly joint filling between column/ beam & block work | Copinig size should in line & level | All Chaukat of each block should in plumb ,line & level with properly fitting of hold fast & column patti | Upto lental level | All lintel ,chajja & loft should in plumb ,line & level and to maintain the thickness as required | Fitting lintel to Beam bottom block work | Every joint of block work should be Properly fill up | All window grill & railing of each block should in plumb ,line & level with properly fitting of hold fast & column patti | Cleaning of window ,Railing and door frame | CURING
3
Inside plaster/Gypsum | bar: Hall N to C Bedroom E
|  | PARTICULER | LEAKAGE CHECKING | Hall N: WATERING BEFORE ONE DAY OF PLASTERING; Hall S: LOCATION OF ELECTRICAL FITTING is at proper position as per electric layout drawing; Hall E: MESH FITING AT B/W & R.C.C JOINT; Hall W: MORTOR PROPORTION; Kitchen S: CEMENT SLURRY APPLICATION ON R.C.C WORK; Kitchen E: THIYYAS FOR PLASTER THIKNESS CHECKING; Kitchen W: PLASTER CHECKING; M Bedroom W: 5'' PLASTER CUTTING FOR SKIRTING IN LINE AND LEVEL; C Bedroom N: CLENING OF WINDOW AND DOOR FRAME; C Bedroom S: CURING; C Bedroom E: FAN HOOK
[7 empty] | CEILING | WALL |  |  | LINE | DHAR | LEVEL | RIGHT ANGLE
HALL
C.BED
M.BED
KITCHEN
C.TOILET
A.TOILET
Wash
HALL
C.BED
M.BED
KITCHEN
C.TOILET
A.TOILET
Wash
4
|  | Reinforcement work for Lintel & Loft |  | M Bedroom N: Casting work for Lintel & Loft
|  | Room Name | Short Direction Bar/Alt Chimta (Where Long bar is not rest on simply supported wall) | Hall E: Short Direction Bar Bottom (Where Long bar is rest on simply supported wall); Kitchen S: Long Direction bar(Simply supported wall); M Bedroom N: Room Name; M Bedroom S: Concrete material proportion; M Bedroom E: Proper mixing of concrete; M Bedroom W: at the time of conreting plz check proper covering at all side; C Bedroom N: Hammer/vibrate the concrete of all side; C Bedroom S: Check proper smoth finish at the top of the loft
|  |  | dia. of bar | Hall N: Spacing; Hall S: Check; Hall E: dia. of bar; Hall W: Spacing; Kitchen N: Check; Kitchen S: dia. of bar; Kitchen E: Spacing; Kitchen W: Check
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
|  | Bed-1 |  | M Bedroom N: Bed-1
|  | Bed-2 |  | M Bedroom N: Bed-2
|  | Kitchen |  | M Bedroom N: Kitchen
10 | Fabrication work | 1 and 2
Grill Fitting and Balcony railing | bar: Hall N to Kitchen W
|  | Size of window/ventilator |  | Hall N: check all Grill /Ventilator size and design as per given drawing; Hall S: Check Primer coat should be done before fitting of all Grill /Ventilator.; Hall E: Check grinding of every welded joint should be properly smoth of all Grill /Ventilator.; Hall W: check Grill /Ventilator fitting in proper position 1'' inside from outer face of the wall; Kitchen N: Grill fitting hole break properly; Kitchen S: Grill level check by tube level; Kitchen E: Grill should be fit in line & plumb (gola); Kitchen W: Filling hole proper level & finishing
|  | L | H
11 | Painting | 1 |  | Kitchen E: 2
|  | Granding (1.0/sft) And Putti-1 (1.25/ sft) |  | Kitchen E: Putti-2 with Final Base (1.25/ sft) And Ghassai + Primer(1.0/ sft)
|  | Ghasai work should be completed | 1st coat Putti work is properly done or not | Hall N: Check if all other adjacent work are completed; Hall S: Check the scaffolding is safe and scartch free; Hall E: Prior to application of putty has the desire surface has been vetted; Hall W: Check for cleaning of wall and cutting surface its free from dead mortar,dust,nails,oil,grease; Kitchen N: Check for Effloresces; Kitchen S: Ensure Applicationhas done on entire area including skirting notch,opeining etc; Kitchen E: Fill crack seal wherever cracks are seen by making "v" groove; Kitchen W: 2nd coat Putti work is properly done or not; M Bedroom N: After crack filling and ghasai work then applied primer; M Bedroom S: Check surface after 2nd coat putty application is even; M Bedroom E: Ensure sanding before primer application; M Bedroom W: Whether the consisrency of primer applied on walls and ceiling
3
|  | Paint coat- 1(0.75/ sft) |  | Hall N: Paint coat- 2(0.75/ sft); Hall E: Texture (1.0/ sft); Kitchen N: Oil paint = Door Frame+Grill+Railing; Kitchen W: Cleaning 100%
|  | Pre-Inspection Material Confirming to approval shade/make for wall,ceiling to kadapa rack door frame | Check for primer application (Alkali resistance) and mixing ratio | Hall N: Painting mixing ratio; Hall S: Check for any surface undulation before application, do if any touch required; Hall E: Post Painting Ensure all the edges of plaster / Rcc work in lines and level; Hall W: Check for uniform application on all wall mitigate shade variation if any; Kitchen N: Mark of paint raler / brush shall not be observable; Kitchen S: cleaning of paint marks in entire flat on window,floor etc.; Kitchen E: After colouring plz check that the door frame and window grills and flat is cleaned or not; Kitchen W: Remove excess material from chaukhat and grill then apply primer and paint; M Bedroom N: At the time of colouring plz check any variation occurred or not in colour
12 | Finishing- W | Aluminium Window Fitting | bar: Hall N to C Bedroom N
|  | Discription | Grill Fitting | Hall N: Frame Screw; Hall S: TPI Baring; Hall E: Lock/ Handle; Hall W: Glass Bedding; Kitchen N: Track Bedding; Kitchen S: Drainage Hole; Kitchen E: Paper Removing; Kitchen W: Glass Cleaning; M Bedroom N: Properly Sliding; M Bedroom S: Sealicon sealent filling; M Bedroom E: L; M Bedroom W: H; C Bedroom N: Quantity
HALL
M.BED
C.BED
BED - COOLER
KITCHEN
A.TOILET
C.TOILET
Silding window door
13 | Finishing-D | Door Panels fitting | bar: Hall N to M Bedroom S
|  | Room Name | Hinges | Hall N: Aldrop; Hall S: Tadi; Hall E: Tadi; Hall W: Tawer Bolt; Kitchen N: Handle; Kitchen S: Baby Latch; Kitchen E: Is it door properly close & open; Kitchen W: Screw of all Acceseries door is properly fittited; M Bedroom N: Tower bolt ,Tadi & door aldrop properly fitting in hole; M Bedroom S: is it stopper fitting is ok
|  |  | Hinges | Hall N: Bed & Main door; Hall S: Bed & Main door; Hall E: Balcony & Toilet door; Hall W: Bed & Main door; Kitchen N: All door
|  |  | ___ X __ X __mm | Hall N: __mm-__''; Hall S: __mm-__''; Hall E: __mm-_''; Hall W: __mm__''; Kitchen N: __''; Kitchen S: Toilet
Hall
C.Bed
M.BED
C.TOILET
A.Toilet
BATH
KITCHEN
Balcony